## Current
R02 - Risk Assessment Register (ISO9001: 2015 Clause 6.1)
1 | 2 | 3 | 4 | 5 |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Probability of Occurrence
Risk No | Identified Risk/ Opportunity | Owner | Description of Risk (potential consequences) | Likely | Probable | Unlikely | Risk Level | Priority | Control Measures | Mitigation Level | Actions to address risk/opportunity | How to integrate/implement actions | Evaluate effectiveness | Review Date
1 | Wrong material or mislabeled material | Dillian Richardson | material mislabeled by supplier could cause line shut down and producing bad parts . |  |  | x | Low | 2 | CofA required and inspected, changed to a primed branded material, manufacturer labels material. | Mitigate | supplier audits, CofA requirement and inspection, communication to supplier | Process audit facilitated by QM
2 | Truck with supplied material arrives late | John Stevens | Due to bad weather or lack of drivers the truck could arrive late causing on-time completion to be missed |  |  | x | Low | 1 | ETA is sent by supplier and monitored by shipping and receiving. | Mitigate | Delivery reports from the distributor, supplier audits to understand the process and provide appropriate corrective actions, Warehouse was moved to a local location to enable pick-up if necessary.
3 | Damaged gaylord at shipment receipt | Dillian Richardson | If forklift drivers are wreckless in the material handling process, material is wasted and possible contamination. |  |  | x | Low | 1 | Evaluations a license renewal. | Mitigate | Forklift training, corrective actions and investigation process if issue occurs
4 | Staffing shortage | Dave Grambling | If there is a shortage of staff then lines could shut down and efficiency goes down. |  | x |  | Medium | 3 | Employee rewards/incentives for exceptional attendance | Mitigate | Designate fill-in or overtime employee | Get with operators and create monthly schedule, communicate the fill-in employee
5 | Shortage turnover | Dave | If there is high employee turnover then then lines could shut down and efficiency goes down. Knowledge drops and quality decreases |  | x |  | Medium | 3 | Pay increase, promote within, employee referral program | Mitigate | Feedback to staffing agency on temps (attendance, time-management, attention to detail) | Complete evaluation form to be completed at 2-week mark.
6 | COVID pandemic | Rodney | If employees get COVID-19, then there is a staffing shortage. |  | x |  | High | 1 | Temperatures are taken across three shifts and information is charted. Monthly disinfection of facility, Encourage social distancing and masks are available. | Mitigate | Temperatures are taken across three shifts and information is charted. Encourage social distancing and masks are available.
7 | Outsourcing molders
8
9
10
11
12
13
14
15
16
17
18
19
20

## Risk Assessment Key
No. | Heading | Description | Clause
1 | Risk Identification Number | Control number applied to a particular risk
2 | Identified Risk/Opportunity | Description of the risk/opportunity in question
3 | Owner | Person responsible for the risk control - usually department manager
4 | Description of Risk (potential consequences) | A short description of the possible damage caused by the occurrence of the risk or opportunity
5 | Probability of Occurrence | The risks can be categorized as very likely, probable and unlikely based on the likelihood of these risks cropping up, where, for example: 1. Likely. Means 70-100% chances of its occurrence; 2. Probable. Means 30-70% chances and 3. Unlikely. Can be used for risks which have less than 30% chance of occurrence
6 | Risk Level | The level of the risk can be categorized as High, Medium and Low depending on how critical the risk and its effects can be
7 | Risk Priority | Based on the probability of occurrence then the intensity of the impact, the risk factors can be assigned a priority level using a scale ranging from 1 to 5, where 1 means high priority and 5 means least important
8 | Control Measures | The policies, procedures and resources which are already available to prevent or reduce the impact of the risk or address the opportunity. Information on the applied control measures to treat the identified risk/opportunity; as required by Clause 6.1.2 ISO9001: 2015
9 | Mitigation Level | After analyzing all the aspects of the risk/opportunity and the existing preventive measures that can be used, the project team needs to decide on the mitigation strategy to deal with the risk/opportunity. There can be four different mitigation strategies: 1) Transfer: In this the risk is managed by transferring the risk handling to a third party or agency; 2) Mitigate: Devise a plan and work out strategies so as to prevent, minimize or bypass the risk; 3) Avoid: This strategy is used when the risk factor does not pose any considerable threat; the basic idea here is to ignore the risk, do nothing; 4) Accept: Accept the consequences
10 | Actions to address R/O | This field needs to be filled in with details of the actions required
11 | How to integrate/implement | This should detail how the organization plans to integrate/implement agreed actions
12 | Evaluate Effectiveness | Details of the review carried out on the effectiveness of the actions taken; usually minuted at Management Review
13 | Review Date | Date at which the original risk control measures will be reviewed for effectiveness
For 5 & 6 see Risk Evaluation tab

## Risk Evaluation
LEVEL OF RISK |  | PROBABILITY OF OCCURRENCE
|  | UNLIKELY | PROBABLE | LIKELY
RISK LEVEL | LOW | Trivial = 1 | Tolerable = 2 | Moderate = 3
| MEDIUM | Tolerable = 2 | Moderate = 3 | Substantial = 4
| HIGH | Moderate = 3 | Substantial = 4 | Extreme = 5
Risk Levels 1 & 2: |  | Trivial and Tolerable: | Acceptable and will be monitored
Risk Levels 3: |  | Moderate: | Unacceptable and will be controlled
Risk Level 4: |  | Substantial: | Unacceptable and will be controlled
Risk Level 5: |  | High Priority: | Unacceptable and will be controlled