## Sheet1
FAILURE MODE & EFFECT ANALYSIS
Document No |  | Issue date: |  |  |  | Revision No: |  |  | Revision date:
Process: |  |  | Process owner: |  |  | Project ID: |  |  |  | Project title:
Identify process steps | How can the process go wrong? | What is the impact if it goes wrong | How severe? | What could cause the failure to occur? | OCCURENCE of causes | What controls exist to prevent or detect? | Rate of detect | SEVxOCCxDET | What are the actions for reducing the occurrence of the causes or for improving the detection |  |  | What were the actions implemented
Process Step (Or product part) | Potential Failure Mode | Potential Failure Effect | SEV | Potential Causes | OCC | Current Controls (prevention/detection) | DET | RPN | Recommended Corrective Action |  |  | Corrective Action
[9 empty] | What? | Who? | When? | Action Taken | SEV | OCC | DET | RPN
Take order | Missing of some required information | Incorrect order | 3 | Lack of attention (taking orders) | 4 | Using of an order-taking checklist | 2 | 24 | Provide stronger validation (order taking system)
Prepare order | Wrong amount of ingredients | Defective product | 4 | Broken of equipment or measurement instr. | 1 | Periodic inspection of equipment or instr. | 3 | 12 | -
" | " | " | 4 | Lack of attention (mixing of ingredients) | 3 | Inspection of product before delivery | 4 | 48 | Buy hi-tech inspection device
Deliver order | Wrong customer address | Missed delivery | 4 | Lack of attention (taking orders) | 3 | Using of a customer tracking system | 1 | 12 | -
" | Takes too long to deliver products | Delayed delivery | 3 | Traffic jam or too many orders | 3 | Using of GIS technology | 3 | 27 | Hire more people to delivery and buy more delivery cars